## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | Sprint 1 | US-001 | Project Requirement Analysis | MUST HAVE | No Dependency | bhavana, rahul, priya | 3 - Completed
S1 | Sprint 1 | US-002 | Finalize Technology Stack | MUST HAVE | Project Architecture Diagram | rajesh, naveen, malini | 3 - Completed
S2 | Sprint 1 | US-003 | System Architecture Design | MUST HAVE | Project Architecture Diagram | sandeep, oneeka, irfana | 3 - Completed
S2 | Sprint 1 | US-004 | GitHub & Project Structure Setup | MUST HAVE | GitHub Repository Setup | priya, rajesh, oneeka | 3 - Completed
S3 | Sprint 2 | US-005 | JWT Authentication | MUST HAVE | Node.js & Express Setup | rahul, rajesh, naveen | 3 - Completed
S3 | Sprint 2 | US-006 | MongoDB Configuration | MUST HAVE | MongoDB Atlas Configuration | rajesh, naveen, priya | 3 - Completed
S4 | Sprint 2 | US-007 | AbuseIPDB API Integration | MUST HAVE | AbuseIPDB API Key | sandeep, rahul, irfana | 3 - Completed
S4 | Sprint 2 | US-008 | AlienVault OTX Integration | MUST HAVE | AlienVault OTX API Key | malini, oneeka, sandeep | 3 - Completed
S5 | Sprint 3 | US-009 | Threat Simulation Engine | MUST HAVE | AbuseIPDB Blacklist Data | rahul, naveen, sandeep | 3 - Completed
S5 | Sprint 3 | US-010 | Socket.IO Broadcasting | MUST HAVE | Socket.IO Setup | oneeka, malini, rajesh | 3 - Completed
S6 | Sprint 3 | US-011 | Global Threat Map | MUST HAVE | Mapbox | oneeka, malini, irfana | 3 - Completed
S6 | Sprint 3 | US-012 | Dashboard Visualizations | MUST HAVE | Recharts Library | naveen, rahul, priya | 3 - Completed
S7 | Sprint 4 | US-013 | MITRE ATT&CK Mapping | SHOULD HAVE | MITRE ATT&CK Dataset Mapping | irfana, rajesh, rahul | 3 - Completed
S7 | Sprint 4 | US-014 | Nmap Scan Module | MUST HAVE | Nmap Installation | irfana, naveen, sandeep | 3 - Completed
S8 | Sprint 4 | US-015 | IP Reputation Module | MUST HAVE | AbuseIPDB API | malini, oneeka, priya | 3 - Completed
S8 | Sprint 4 | US-016 | QR / URL Scanner | SHOULD HAVE | AlienVault OTX API | bhavana, rahul, rajesh | 3 - Completed
S9 | Sprint 5 | US-017 | AI Assistant | MUST HAVE | Gemini / OpenRouter API Key | naveen, rahul, bhavana | 3 - Completed
S9 | Sprint 5 | US-018 | RAG Knowledge System | SHOULD HAVE | knowledge.json (RAG Dataset) | naveen, rajesh, priya | 3 - Completed
S10 | Sprint 5 | US-019 | Dockerization | MUST HAVE | Docker Setup | priya, sandeep, rajesh | 3 - Completed
S10 | Sprint 5 | US-020 | Nginx Configuration | SHOULD HAVE | Nginx Reverse Proxy | sandeep, naveen, oneeka | 3 - Completed
S11 | Sprint 5 | US-021 | Role-Based Dashboard | MUST HAVE | JWT Authentication | oneeka, malini, rahul | 3 - Completed
S11 | Sprint 5 | US-022 | Data Optimization | SHOULD HAVE | MongoDB Optimization Queries | rajesh, naveen, priya | 3 - Completed
S12 | Sprint 5 | US-023 | System Testing | MUST HAVE | Integrated Module Testing | rahul, oneeka, irfana | 3 - Completed
S12 | Sprint 5 | US-024 | Agile Documentation | MUST HAVE | Project Documentation | bhavana, malini, priya | 3 - Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (Hours) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
US-001 | 1 | Project Requirement Analysis | 2026-01-05 | 2026-01-06 | bhavana, rahul, priya | Planning | 3-Completed | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0
US-002 | 2 | Finalize Technology Stack | 2026-01-06 | 2026-01-07 | rajesh, naveen, malini | Planning | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-003 | 3 | System Architecture Design | 2026-01-07 | 2026-01-08 | sandeep, oneeka, irfana | Design | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-004 | 4 | GitHub & Project Structure Setup | 2026-01-09 | 2026-01-10 | priya, rajesh, oneeka | Setup | 3-Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | JWT Authentication | 2026-01-13 | 2026-01-14 | rahul, rajesh, naveen | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-006 | 6 | MongoDB Configuration | 2026-01-15 | 2026-01-16 | rajesh, naveen, priya | Coding | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-007 | 7 | AbuseIPDB API Integration | 2026-01-16 | 2026-01-17 | sandeep, rahul, irfana | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-008 | 8 | AlienVault OTX Integration | 2026-01-18 | 2026-01-19 | malini, oneeka, sandeep | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-009 | 9 | Threat Simulation Engine | 2026-01-21 | 2026-01-22 | rahul, naveen, sandeep | Coding | 3-Completed | 14 | 5 | 5 | 4 | 0 | 0 | 0 | 0
US-010 | 10 | Socket.IO Broadcasting | 2026-01-23 | 2026-01-24 | oneeka, malini, rajesh | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-011 | 11 | Global Threat Map | 2026-01-24 | 2026-01-25 | oneeka, malini, irfana | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-012 | 12 | Dashboard Visualizations | 2026-01-26 | 2026-01-27 | naveen, rahul, priya | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-013 | 13 | MITRE ATT&CK Mapping | 2026-01-29 | 2026-01-30 | irfana, rajesh, rahul | Coding | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-014 | 14 | Nmap Scan Module | 2026-01-31 | 2026-02-01 | irfana, naveen, sandeep | Coding | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-015 | 15 | IP Reputation Module | 2026-02-02 | 2026-02-03 | malini, oneeka, priya | Coding | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-016 | 16 | QR / URL Scanner | 2026-02-03 | 2026-02-04 | bhavana, rahul, rajesh | Coding | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-017 | 17 | AI Assistant | 2026-02-06 | 2026-02-07 | naveen, rahul, bhavana | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-018 | 18 | RAG Knowledge System | 2026-02-07 | 2026-02-08 | naveen, rajesh, priya | Coding | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-019 | 19 | Dockerization | 2026-02-09 | 2026-02-10 | priya, sandeep, rajesh | DevOps | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-020 | 20 | Nginx Configuration | 2026-02-10 | 2026-02-11 | sandeep, naveen, oneeka | DevOps | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-021 | 21 | Role-Based Dashboard | 2026-02-11 | 2026-02-12 | oneeka, malini, rahul | Coding | 3-Completed | 10 | 3 | 3 | 4 | 0 | 0 | 0 | 0
US-022 | 22 | Data Optimization | 2026-02-12 | 2026-02-12 | rajesh, naveen, priya | Optimization | 3-Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0
US-023 | 23 | System Testing | 2026-02-12 | 2026-02-13 | rahul, oneeka, irfana | Testing | 3-Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-024 | 24 | Agile Documentation | 2026-02-13 | 2026-02-13 | bhavana, malini, priya | Documentation | 3-Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 (07-Jan) | Confusion in finalizing system architecture design | Conducted team discussion and finalized microservice separation
Sprint 1 | Day 5 (09-Jan) | GitHub branching conflicts during setup | Standardized branch naming and resolved merge conflicts
Sprint 1 | Day 7 (11-Jan) | Initial environment configuration mismatch across systems | Unified development environment configuration
Sprint 2 | Day 10 (14-Jan) | JWT token validation inconsistency | Fixed middleware logic and standardized token structure
Sprint 2 | Day 12 (16-Jan) | MongoDB schema mismatch with authentication module | Updated schema and synchronized backend validation
Sprint 2 | Day 14 (18-Jan) | AbuseIPDB API rate-limit issue | Implemented caching and scheduled API calls
Sprint 2 | Day 15 (19-Jan) | AlienVault OTX response structure inconsistency | Added response filtering and validation logic
Sprint 3 | Day 18 (22-Jan) | Threat simulation producing duplicate data | Improved pattern randomization logic
Sprint 3 | Day 20 (24-Jan) | Socket.IO not broadcasting updates properly | Fixed namespace and event listener configuration
Sprint 3 | Day 22 (26-Jan) | Dashboard charts showing delayed updates | Optimized MongoDB aggregation queries
Sprint 4 | Day 25 (29-Jan) | MITRE mapping logic not aligning with threat categories | Refactored mapping logic and standardized labels
Sprint 4 | Day 27 (31-Jan) | Nmap scan returning inconsistent results | Improved subnet validation and scan handling
Sprint 4 | Day 29 (02-Feb) | QR scanner allowing unsafe redirects | Implemented strict URL sanitization rules
Sprint 5 | Day 33 (06-Feb) | AI assistant generating unrelated responses | Restricted context and implemented RAG filtering
Sprint 5 | Day 35 (08-Feb) | RAG retrieval returning irrelevant documents | Refined embedding search logic
Sprint 5 | Day 37 (10-Feb) | Docker containers not connecting to correct DB | Corrected environment variables and seeded database
Sprint 5 | Day 39 (12-Feb) | Performance slowdown during final testing | Added indexing and optimized database queries
Sprint 5 | Day 40 (13-Feb) | Documentation formatting inconsistencies | Standardized documentation structure and finalized report

## Retrospection
Sprint # | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-05 | 2026-01-12 | All Team Members | Clearly defining requirements and architecture before coding | Starting development without finalizing environment setup | Daily sync meetings and collaborative planning | Finalized architecture, resolved Git conflicts, standardized environment configuration
2 | Sprint 2 | 2026-01-13 | 2026-01-20 | All Team Members | Implement structured backend modules with validation and proper schema mapping | Making API calls without rate-limit handling | Backend and API collaboration | Implemented JWT fixes, optimized MongoDB schema, added API caching and response validation
3 | Sprint 3 | 2026-01-21 | 2026-01-28 | All Team Members | Improve real-time simulation and dashboard responsiveness | Using static mock data for frontend validation | Cross-team testing during feature integration | Optimized Socket.IO broadcasting, improved simulation logic, enhanced dashboard query performance
4 | Sprint 4 | 2026-01-29 | 2026-02-05 | All Team Members | Strengthen security modules and threat validation mechanisms | Ignoring edge cases in scan validation | Code reviews before merging security features | Improved Nmap validation, enhanced MITRE mapping accuracy, secured QR scanner
5 | Sprint 5 | 2026-02-06 | 2026-02-13 | All Team Members | Focus on AI accuracy, deployment stability and final system optimization | Testing AI without domain restriction logic | Performance monitoring and collaborative testing | Implemented RAG filtering, fixed Docker configuration, optimized database indexing, completed system testing and documentation